## Sheet1
Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact | Risk Factor | Risk Mitigation | Person in Charge
Deployment | The deployement of the tomcat application on the dedicated server could cause issues | 80% | 10 | 8 | Early testing with non complete builds. Automated deployment | Philipp
Time Issues | The fact that we could run into time problems for implementing our UCs due to exams | 70% | 10 | 7 | Start working on it early | Philipp
Wrong focus | Focusing to much on details instead of the whole picture could lead to missing functionality/time | 70% | 5 | 3.5 | Constant syncs + time tracking | Philipp
Software updates | Programs or tools could update (like youtrack) loosing functionality | 25% | 8 | 2 | Try to not update if not necessary and possible | Florian
Git issues | Missuse of git could lead to data loss | 20% | 8 | 1.6 | Use git accordingly | Florian
Privat Issues | Due to some illness or personal circumstances one or more team members could not be fully available to the team | 15% | 9 | 1.35 | Nothing we can really do about it. The others have to compensate the loss | Jonas
Not usable | Tool is not usable by end users | 10% | 9 | 0.9 | Functionality tests from different people | Jonas
Hardware issues | One of the laptops or the Server could have hardware issues | 5% | 9 | 0.45 | Server has redundant components. Laptops are to be used carefully. Companies offer replacements in case of failure | Everyone according to who it affects
Data Security laws | With the current european general data potection regulation it can be next to impossible to cope with it running the website on a private webserver | 100% | 10 | 10 | One mitigation would be to negotiate with Ms. Berkling that she will install it locally on her computer for grading | Everyone
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0